## Dashboard
PROJECT MANAGEMENT DASHBOARD
| Total Projects | In Progress | Completion Rate | Overdue Tasks
| 3 | 2 |  | 0
| Done | 3
| In Progress | 3
| Review | 1
| To Do | 5

## Projects
PROJECT OVERVIEW
Project Name | Description | Owner | Start Date | Due Date | Status | Priority | Budget | Spent | % Complete
Website Redesign | Complete overhaul of company site | Sarah | 2026-01-15 | 2026-04-30 | In Progress | High | 25000 | 12500 | 50%
Mobile App v2 | Native app rebuild | Mike | 2026-02-01 | 2026-06-30 | In Progress | High | 40000 | 8000 | 20%
CRM Integration | Connect CRM to all systems | Lisa | 2026-03-01 | 2026-05-15 | Not Started | Medium | 15000 | 0 | 0%

## Task Board
TASK BOARD
Task | Project | Assignee | Status | Priority | Due Date | Est Hours | Actual Hours | Notes
Design mockups | Website Redesign | Sarah | Done | High | 2026-02-01 | 16 | 18 | Approved
Frontend build | Website Redesign | Tom | In Progress | High | 2026-03-15 | 40 | 20 | React
Backend API | Website Redesign | Mike | In Progress | High | 2026-03-20 | 32 | 12 | REST
Content migration | Website Redesign | Lisa | To Do | Medium | 2026-04-01 | 20 | 0 | 500+ pages
UI/UX research | Mobile App v2 | Sarah | Done | High | 2026-02-15 | 24 | 22 | Done
App wireframes | Mobile App v2 | Sarah | In Progress | High | 2026-03-01 | 20 | 15 | 80%
iOS development | Mobile App v2 | Tom | To Do | High | 2026-04-15 | 80 | 0 | Swift
Android dev | Mobile App v2 | Mike | To Do | High | 2026-04-15 | 80 | 0 | Kotlin
API integration | Mobile App v2 | Mike | To Do | Medium | 2026-05-01 | 40 | 0 | REST+WS
Requirements doc | CRM Integration | Lisa | Review | High | 2026-03-10 | 8 | 6 | In review
Vendor evaluation | CRM Integration | Lisa | To Do | Medium | 2026-03-20 | 16 | 0 | 3 vendors
Data mapping | CRM Integration | Tom | To Do | Medium | 2026-04-01 | 24 | 0 | Fields
TOTALS

## Meeting Notes
MEETING NOTES
Date | Project | Attendees | Agenda | Decisions | Action Items | Owner | Due Date
2026-01-20 | Website Redesign | Sarah, Tom, Mike | Kickoff | Approved timeline | Create design system | Sarah | 2026-02-01
2026-02-05 | Mobile App v2 | Sarah, Tom, Mike | UX research | Go native | Start wireframes | Sarah | 2026-02-15
2026-03-01 | CRM Integration | Lisa, Tom | Requirements | Salesforce primary | Draft requirements | Lisa | 2026-03-10

## Resources
RESOURCE TRACKER
Team Member | Role | Projects | Allocated Hours | Available Hours | Utilization
Sarah | Design Lead | Website, Mobile App | 36 | 40
Tom | Frontend Dev | Website, Mobile App, CRM | 38 | 40
Mike | Backend Dev | Website, Mobile App | 32 | 40
Lisa | PM | CRM, Website | 24 | 40

## Instructions
HOW TO USE YOUR PROJECT MANAGEMENT BOARD
Getting Started
1. Add projects to Projects tab
2. Break work into tasks in Task Board
3. Track team in Resources
4. Log meetings in Meeting Notes
5. Monitor on Dashboard
Status Flow
To Do -> In Progress -> Review -> Done
Update daily for accuracy
Tips
- Keep tasks 2-8 hours each
- Update % complete weekly
- Watch utilization to prevent burnout
Need Help?
Message us on Etsy!